## !FAQ
Q: What is the purpose of this file and how I should use it? (please, read me first!)
A: This is a template to help you estimate delivery expenses and project cost for services projects. File contains all important variables to account necessary cost items into project cost. File contains three sheets to gradually lead you through project cost estimation. 1. Start from "Project overview" sheet to fill details about customer, project, requirements and pre-sale team. 2. Once done, move forward with effort estimations on sheet "Project estimations_adv". Specify scope of work, select proper resources, estimate tasks by man manhours and risks, select required percentage of architect and project manager involvement, put partner cost if necessary. If you need to overview the resources total man hours and cost by roles you may switch to the "Resources overview" sheet. 3. Once you complete estimations, go back to the sheet "Project overview" to finalize the key project parameters: project scope and timeline, additional expenses. Check project budget, commercials, choose required margin level and review recommended project price. All sheets in the file are designed with the same colour approach:
Fields where you input is required are pink colored;
Fields where values are automatically calculated have grey color. Please do not make any changes in these fields.
Q: How should I estimate project duration?
A: To estimate project duration definition of the project scope is required: you need to understand which tasks or stages will be performed one by one, and which can be done in parallel. Based on that you will be able to estimate project duration. For project duration estimation we recommend to use consideration as 1 day = 6 engineer hours. This is because engineer should have some time availabe during the day for pre-sale, learning and some internal activities. If you're unsure about project duration estimation you may ask project manager to help. Example: let's say we have a total estimations for project = 80 hours with 4 stages in scope. Each stage will take 20 hours to be completed. Stages 1, 2, 3 should be done one by one, but stage 4 will be done in parallel with stage 3 (second engineer will participate). Thus, our duration will be 20 hours * 3 time stages = 60 hours / 6 hours a day = 10 business days.
Q: What is the difference between simple and advanced estimations template?
A: 2.1 Simple estimations template is recommended to use for typical projects up to 15.000$. Your estimations in this case come from initial understanding of approximate cost of the project and previous experience. Using this template you may estimate efforts by stages in man days. 2.2 Advanced estimations template is recommended for custom project with cost > 15.000$. In this case you probably don't know the project cost at the beginning and your estimations will be prepared through thinking about necessary tasks and efforts required for each of them.

## 2a.Travel calc (hidden)
Travel expenses calculator
| Customer name | #NAME? |  | Date | 2018-11-09
| Project name | #NAME? |  | Prepared by
Fill only fields like |  | Yellow
| From | Russia
| To | Malaysia
№ | Expense | Category | Value
1 | Total working hours to be spent onsite |  | 0
2 | Number of persons in the business trip |  | 1
3 | Total working days in the buisiness trip for 1 person |  | 0
4 | Per diems |  | #REF!
5 | Accommodation expenses | INT_Category 1 | #REF!
6 | Round trip tickets (train, avia, etc) |  | 1000
7 | Project manager trips for onsite kick-offs and other meetings | 0 | 2
8 | Other travel expenses * |  | 0
9 | Reserve for not identified risks ** |  | 10%
Total buisiness trip expenses, $ |  |  | #REF!
| * - Other travel expenses includes: - Train to/from airport expenses - Taxi expenses - Purchase of consumables for a project needs - Car rent - Other expenses | ** - Not identified risks includes: - Trip tickets value changes - Additional transport expenses and taxes - Unplanned taxi expenses in the case of force majeure - Additional airport/railway station rates and taxes - Other unplanned expenses (В случае вопросов по данному пункту уточните у Руководителя проекта)

## PM-PA catalog (hidden)
Project Management Cost Calculator
Performed measures | Labor costs, h | Quantity | Total, h | Notes
Project initiation
Analysis of the input data, the acceptance of the project from the Solution Sale | 1 | 1 | 1 | one-time
Estimate man-hours on project management, calculate business trips and other expenses, risks reservation | 2 | 1 | 2 | one-time
Preparing project plan with timelines (depending of project duration) | 1 | 1 | 1 | one-time
Preparing initial list of risks with action plan for each | 2 | 1 | 2 | one-time
Prepare (and agree on) spending budget of the project and cash flow plan | 2 | 1 | 2 | one-time
Filling in the FS, negotiating the contract with the customer | 2 | 1 | 2 | one-time
Project accounting in corporate information systems
Creating an estimate in 1C | 0 | 1 | 0 | one-time
Creating a Project Plan on Project Server | 1 | 1 | 1 | one-time
Creation of a project card and communication plan in CRM | 0 | 1 | 0 | one-time
Audit of the project start stage | 0 | 1 | 0 | one-time
Project start
Formation of the project team | 2 | 1 | 2 | one-time
Formation of project documentation | 0 | 1 | 0 | one-time
Internal installation meeting (+ protocol) | 2 | 1 | 2 | one-time
External installation meeting (+ protocol) | 2 | 1 | 2 | one-time
Setting tasks, starting work | 1 | 1 | 1 | one-time
Work with subcontractors
Search and attraction of subcontractors, meetings and discussions | 1 | #REF! | #REF! | one-time, by the number of contractors
Execution of an application for a subcontractor | 1 | #REF! | #REF! | one-time, by the number of contractors
Alignment of the contract with the subcontractor | 2 | #REF! | #REF! | one-time, by the number of contractors
Installation meeting, setting tasks | 1 | #REF! | #REF! | one-time, by the number of contractors
Monitoring and control
Internal discussion of the status of the project, informing | 1 | #REF! | #REF! | weekly
External discussion of the status of the project, informing | 1 | #REF! | #REF! | weekly
Solving operational issues with the project team | 1 | #REF! | #REF! | weekly
Solving operational issues with the customer | 1 | #REF! | #REF! | weekly
Risk management | 1 | #REF! | #REF! | weekly
Updating the project plan, recording labor costs | 1 | #REF! | #REF! | weekly
Hardware logistics control | 1 | #NAME? | #NAME? | weekly
Project handover
Acceptance of works from subcontractors | 2 | #NAME? | #NAME? | one-time (for each subcontractor)
Execution of acceptance and transfer acts of works with a subcontractor | 1 | #NAME? | #NAME? | one-time (for each subcontractor)
Payment for subcontractor's works, making applications in 1C | 0.5 | #NAME? | #NAME? | one-time (for each subcontractor)
Participation in the UAT | 2 | 1 | 2 | one-time
Registration of documents and delivery to the customer | 2 | #NAME? | #NAME? | one-time
Execution of acceptance and transfer acts of works with a customer | 2 | 1 | 2 | one-time
Customer questioning | 0.5 | 1 | 0.5 | one-time
Closing the project in corporate information systems
Creation of actual data on the estimate in 1C | 0.5 | 1 | 0.5 | one-time
Updating the project card in CRM, transferring the project to the archive | 0.5 | 1 | 0.5 | one-time
Project completion
Audit of project completion stage | 0 | 1 | 0 | one-time
Dissolution of the project team (description of the results, meeting with the team, letter of completion) | 1 | 1 | 1 | one-time
Additional works
Development of additional project reporting for the customer | 0 | 0 | 0
Organization of additional meetings and visits to the customer | 0 | 0 | 0
Additional communication with contractors, organization of working groups | 0 | 0 | 0
Need for organization of access to facilities and coordination of work | 0 | 0 | 0
Other additional works | 0 | 0 | 0
|  | Total hours: | #REF!

## Project overview
Pre-sale team
Account manager | Put account manager's name here
Solution sales | Put solution sales name here
Delivery | Put the name of the one who are estimating the project effort
Project manager | Put project manager name here
[Add more roles if needed] | Add more lines if needed and specify the roles and names
Customer details
Cutomer name | Put customer name here
Customer country
CRM opportunity ID | Indicate CRM opportunity which is related to given estimation
Project details
Project name | Put project name here
Project objectives | Describe the goals and objectives of the potential project, associated business problem and other important details referring project purpose
Project high-level requrements
Project funding source | Describe the revenue streams (customer budget, vendor funding etc.) and specify expected revenue amount from each of them
Summary available project funding, USD | Input the total available sum to fund turn-key solution implementation (services and any required software/hardware)
Customer's requirements and expectations | Describe customer requirements which given project should address (technical, organizational, time-related, financial and any others). Mention everything which may affect project scope, budget, timeline, techical methodolody and approach to project management.
! IMPORTANT ! Key project parameters below should be treated as delivery commitments for a project. They should become the basis of the commercial and technical proposal for the customer.
Project scope
Project scope | Describe key deliverables and specify if anything is out of scope
Project constraints | Describe any constraints that should be agreed with the customer and included into proposal
Internal requirements | Any specific internal requirements for the project
Project timeline
Project timeline | Specify estimated project implementation time | Enter value
Project expenditure budget
In-house delivery resources | 2613.6 | Refer to Estimations - A
Assessed risks | 0 | Refer to Estimations - B
3rd parties/ partners | 0 | Refer to Estimations - C
Project management | 24.948 | Refer to Estimations - D
Business trips | 0 | Enter value
Consumables | 0 | Enter value
Other expenses | 0 | Enter value
TOTAL PROJECT COST/ BUDGET | 2638.548 | Calculation
Commercials
Target margin | 30% | Enter value
Gross profit | 1130.8063 | Calculation
TOTAL PROJECT PRICE (REVENUE) | 3769.3543 | Calculation
Potential contract price
Services revenue | 3769.3543 | Calculation
Licence revenue (reference) |  | Enter value
Hardware revenue (reference) |  | Enter value
TOTAL CONTRACT PRICE | 3769.3543 | Calculation

## Project estimations_adv
Target margin (refer to Project overview)
| A. In-house delivery resources | [6 empty] | 30%
| # | Project implementation tasks | Resource country | Resource role | Rate, USD | Estimated hours | Cost, USD | Revenue, USD | Resource Full Name
| 1 | Requirements & Sample Data Alignment | Malaysia | Engineer | 22 | 4 | 88 | 125.7143 | Malaysia Engineer
| 2 | Azure AI Infrastructure Provisioning | Malaysia | Engineer | 22 | 4 | 88 | 125.7143 | Malaysia Engineer
| 3 | M365 & Power Platform Environment Setup | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 4 | Dataverse Schema & Mock Ledgers | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 5 | OCR Model Calibration | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 6 | GPT-4o Vision Prompt Engineering | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 7 | Process 1 Power Automate Workflows - Build RFP Ingestion | Malaysia | Engineer | 22 | 12 | 264 | 377.1429 | Malaysia Engineer
| 8 | Process 2 Power Automate Workflows - Build Document Intelligence | Malaysia | Engineer | 22 | 12 | 264 | 377.1429 | Malaysia Engineer
| 9 | Teams Adaptive Cards (v1.5) Development | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 10 | Copilot Studio Agent Orchestration | Malaysia | Engineer | 22 | 16 | 352 | 502.8571 | Malaysia Engineer
| 11 | End-to-End System Testing & Tuning | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
| 12 | Strategy & Assessment Collateral | Malaysia | Engineer | 22 | 4 | 88 | 125.7143 | Malaysia Engineer
| 13 | Internal Freeze, Video Recording & Executive Dry Run | Malaysia | Engineer | 22 | 8 | 176 | 251.4286 | Malaysia Engineer
[5 empty] | n/a |  | Check role | Check role
[5 empty] | n/a |  | Check role | Check role
[5 empty] | n/a |  | Check role | Check role
| Total |  |  |  |  | 108 | 2376 | 3394.2857
Estimation accuracy buffer |  | Select appropriate value of the correction level depending of the assumption of the estimation accuracy level, supposition of not assessible risks and other unseen circumstances . This will be added on top of the resource cost as a buffer. |  |  |  |  | Cost, USD | Revenue, USD
10% | [6 empty] | 237.6 | 339.4286
Technical governance - Project architect involvement ratio |  | Estimate overall involvement ratio in %, then choose the approproate role, so this will be applied to overall in-house cost, and estimated hours will be calculated automatically. | Resource country | Resource role | Rate, USD | Estimated hours | Cost, USD | Revenue, USD
10% |  |  |  |  | 0 | 10.8 | 0 | 0
|  |  |  | Total cost of in-house delivery resources |  |  | 2613.6 | 3733.7143
B. Assessed risks
# | Risk name | Risk description | Risk level | Strategy |  |  | Cost, USD | Revenue, USD
1 | Risk #1 | Describe the essense of the risk end it's potential effect | High | Define the strategy to work with the risk (avoidance, mitigation, transfer, acceptance) and describe required actions |  |  | 0 | 0
2 | Risk #2 |  | Medium |  |  |  | 0 | 0
3 | Risk #3 |  | Low |  |  |  | 0 | 0
|  |  |  | Total assesed risks cost |  |  | 0 | 0
C. 3rd parties/ partners
# | Subcontractor | Involvement reason | Scope |  |  |  | Cost, USD | Revenue, USD
1 | Name #1 | Specify the need of given engagament (lack of in-house expertise, certain accreditation is required, cost effectiveness, customer requirement, etc.) | Specify the project scope/ deliverables entrusted to execute by 3rd party |  |  |  |  | 0
2 | Name #2 | Specify the need of given engagament (lack of in-house expertise, certain accreditation is required, cost effectiveness, customer requirement, etc.) | Specify the project scope/ deliverables entrusted to execute by 3rd party |  |  |  | 0 | 0
3 | Name #3 | Specify the need of given engagament (lack of in-house expertise, certain accreditation is required, cost effectiveness, customer requirement, etc.) | Specify the project scope/ deliverables entrusted to execute by 3rd party |  |  |  | 0 | 0
|  |  |  | Total subcontactors cost |  |  | 0 | 0
D. Project management |  |  |  | Subtotal for calculate project management cost |  |  | 2613.6 | 3733.7143
Project management - PM involvement ratio |  | Estimate overall involvement ratio in %, then choose the approproate role, so this will be applied to overall in-house cost, and estimated hours will be calculated automatically. | Resource country | Resource role | Rate, USD | Estimated hours | Cost, USD | Revenue, USD
10% |  |  |  |  | 0.1 | 249.48 | 24.948 | 35.64
Recommendations based on budget subtotal (cell I60) |  |  |  | Total project management cost |  |  | 24.948 | 35.64
below $5000 |  | 10% Project coondinator
from $5000 to $10000 |  | 10% Project manager
from $10000 to $25000 |  | 15% Project manager
above $25000 |  | 20% Project manager
These are median values, you may put any adequate % based on project specifics and complexity

## Resources overview
Project governance overview
Role | Total man hours | Total cost
| 10.8 | 0
| 249.48 | 24.948
Total | 260.28 | 24.948
Project delivery overview
Role | Total man hours | Total cost
0
Malaysia Engineer | 108 | 2376
Total | 108 | 2376 | Right-click on table and "Refresh" to refresh the data

## Reference data
Country |  | Performer country
Argentina |  | Argentina
Brazil |  | Brazil
Bulgaria |  | Bulgaria
Cambodia |  | Cambodia
Chile |  | Chile
Colombia |  | Colombia
Costa Rica |  | Costa_Rica
Croatia |  | Customer
Ecuador |  | Hungary
Egypt |  | India
El Salvador |  | Latvia
Estonia |  | Lithuania
Guatemala |  | Malaysia
Honduras |  | Myanmar
Hungary |  | Peru
India |  | Philippines
Latvia |  | Thailand
Lithuania |  | Vietnam
Malaysia
Mexico
Myanmar
Nicaragua
Thailand
Panama
Paraguay
Peru
Philippines
Romania
Serbia
Slovakia
Slovenia
Turkey
Uruguay
Venezuela
Vietnam
Role
Junior engineer
Engineer
Senior engineer
Architect
Senior architect
Junior developer
Developer
Senior developer
Teamlead
Project management roles
Project manager
Project coordinator
Technical governance roles
Architect
Senior architect
Teamlead
Rate name | Country | Role | Hour rate, USD
ArgentinaEngineer | Argentina | Engineer | 31
BrazilEngineer | Brazil | Engineer | 31
BrazilProject manager | Brazil | Project manager | 29
BulgariaArchitect | Bulgaria | Architect | 75
BulgariaSenior engineer | Bulgaria | Senior engineer | 58
BulgariaProject manager | Bulgaria | Project manager | 63
CambodiaJunior engineer | Cambodia | Junior engineer | 8
CambodiaEngineer | Cambodia | Engineer | 15
CambodiaArchitect | Cambodia | Architect | 51
CambodiaProject coordinator | Cambodia | Project coordinator | 21
CambodiaSenior engineer | Cambodia | Senior engineer | 26
ChileEngineer | Chile | Engineer | 31
ChileProject manager | Chile | Project manager | 29
ColombiaEngineer | Colombia | Engineer | 31
ColombiaArchitect | Colombia | Architect | 41
ColombiaProject manager | Colombia | Project manager | 29
Costa_RicaProject manager | Costa_Rica | Project manager | 29
Costa_RicaEngineer | Costa_Rica | Engineer | 31
CustomerCustomer engineer | Customer | Customer engineer | 0
HungaryArchitect | Hungary | Architect | 75
IndiaArchitect | India | Architect | 21
IndiaEngineer | India | Engineer | 13
IndiaSupport engineer | India | Support engineer | 9
IndiaJunior engineer | India | Junior engineer | 7
IndiaTrainee | India | Trainee | 5
IndiaProject manager | India | Project manager | 18
IndiaSenior engineer | India | Senior engineer | 19
LatviaJunior engineer | Latvia | Junior engineer | 32
LatviaEngineer | Latvia | Engineer | 47
LatviaProject manager | Latvia | Project manager | 63
LatviaArchitect | Latvia | Architect | 75
LithuaniaJunior engineer | Lithuania | Junior engineer | 32
LithuaniaSenior engineer | Lithuania | Senior engineer | 58
LithuaniaProject manager | Lithuania | Project manager | 63
LithuaniaArchitect | Lithuania | Architect | 75
MalaysiaArchitect | Malaysia | Architect | 43
MalaysiaEngineer | Malaysia | Engineer | 22
MalaysiaTrainee | Malaysia | Trainee | 7
MalaysiaJunior engineer | Malaysia | Junior engineer | 16
MalaysiaService delivery manager | Malaysia | Service delivery manager | 49
MalaysiaProject manager | Malaysia | Project manager | 39
MalaysiaSenior engineer | Malaysia | Senior engineer | 31
PeruEngineer | Peru | Engineer | 31
PeruProject manager | Peru | Project manager | 29
PhilippinesJunior engineer | Philippines | Junior engineer | 13
PhilippinesEngineer | Philippines | Engineer | 22
PhilippinesArchitect | Philippines | Architect | 51
PhilippinesProject coordinator | Philippines | Project coordinator | 18
ThailandJunior engineer | Thailand | Junior engineer | 28
VietnamArchitect | Vietnam | Architect | 51
VietnamEngineer | Vietnam | Engineer | 15
VietnamJunior engineer | Vietnam | Junior engineer | 10
VietnamProject manager | Vietnam | Project manager | 26
VietnamSenior engineer | Vietnam | Senior engineer | 23
VietnamSupport engineer | Vietnam | Support engineer | 15

## reference (hidden)
Requirement source | Priority | Author | Complexity | Relevance | Project direction | Industry
Softline | High | Requirements management analyst | High | Actual | Antivirus protection | Automotive industry
Customer | Medium | Pre-sale architect | Medium | Not actual | Informatization objects attestation | Gas industry
| Low | Project architect | Low |  | Audit of computing / network infrastructure | State and municipal sector
|  | Customer |  |  | Audit for compliance with information security requirements | Housing and utilities
|  | Engineer |  |  | Virtualization (Vmware and Microsoft) | Healthcare
|  | Consultant |  |  | Virtual Desktops Ingfrastructure (VDI) | Information Technology
|  | Project manager |  |  | DLP implementing | Light industry
[5 empty] | IDM implementing | Mechanical engineering
[5 empty] | SIEM implementing | Metallurgy
[5 empty] | WAF / DBF implementing | Science and scientific services
|  | Delivery roles |  |  | Information security management system implementing | Oil-producing industry
|  | Engineer |  |  | CIP implementing | Oil refining industry
|  | Analyst |  |  | Delivering applications and balancers | Education
|  | Consultant |  |  | State secrets protection | Food industry
|  | Technical Writer |  |  | Information protectiob in Banking Organizations | Instrument making
|  | Technical Architect |  |  | Trade secret protection | Project institutes
|  | Customer |  |  | Personal data protection | Restaurants and catering
[5 empty] | Microsoft Infrastructure | Agriculture
[5 empty] | Complex Infrastructure Projects | Mass media
[5 empty] | Comprehensive information security projects | Construction, real estate
[5 empty] | Content filtering | Trade
[5 empty] | Provision the security of information in the process control system | Transport
[5 empty] | Provision the activity of the certifying center (CA) | Tourism
[5 empty] | Business continuity provisioning | Coal industry
[5 empty] | Cloud technologies | Pharmaceuticals
[5 empty] | Portal solutions | Finance, credit, insurance, pensions
[5 empty] | Mail systems | Chemical and petrochemical industry
[5 empty] | Countering DDOS attacks | Electrotechnical industry
[5 empty] | Backup | Power engineering
[5 empty] | Servers and storage | Jurisprudence
Network Security
Networks - Routing & Switching
Networks - Unified Communications
Networks - Wireless
Business Intelligence Systems (BI)
Management systems
Database management systems
IT Service Management (ITSM)
Corporate Content Management (ECM)