## Consumption & Hosting Budget
Azure AI Portal – Consumption & Hosting Budget
Estimated budget for the proposed portal, AI processing, automation, and storage services.
Item # | Technical Service | Pricing SKU / Tier | Estimated Unit Usage (incl. Buffer) | Unit Cost (USD) | Line Total (USD) | Billing Unit | Billable Quantity
1.1 | Azure Static Web Apps (Portal Hosting) | Standard Free Tier | 1 Hosted Customer Portal (HTML/React) | 0 | 0 | Hosted portal | 1
1.2 | Azure AI Document Intelligence | Prebuilt Invoice & Layout Model | 1,000 Pages (RFP / PO / Invoice OCR parsing) | 0.01 | 10 | Pages | 1000
1.3 | Azure OpenAI Service (GPT-4o) | gpt-4o Vision Endpoint | 500 Image Triage Calls (~1.5M Tokens) | 5 | 7.5 | Million tokens | 1.5
1.4 | Microsoft Copilot Studio | Copilot Messages / Actions | 2,500 Messages (Capacity Pack Buffer) | 0.008 | 20 | Messages | 2500
1.5 | Power Automate & Dataverse | Process License & Storage | 1 Month Sandbox Process Allocation | 15 | 15 | Month | 1
1.6 | Azure Blob Storage & CDN | Hot Storage & Global CDN | 10 GB Storage & Portal Assets | 0.25 | 2.5 | GB | 10
1.7 | Custom Azure Back-End Infrastructure | Azure Functions / Web Apps | NOT REQUIRED | 0 | 0 | Not required | 0
SUBTOTAL (Base Consumption & Hosting) |  |  |  |  | 55

## Gantt Chart Timeline
Noventiq OpsAgent UOB Summit — Master Project Timeline & Gantt
Project Window: 17 Aug 2026 – 28 Sept 2026 ¦ Internal Freeze: 21 Sept 2026 ¦ Target Event: 28 Sept 2026
[7 empty] | August 2026 | [14 empty] | September 2026
WBS | Phase | Task Description | Start Date | End Date | Duration (Days) | Status | 17 Mon | 18 Tue | 19 Wed | 20 Thu | 21 Fri | 22 Sat | 23 Sun | 24 Mon | 25 Tue | 26 Wed | 27 Thu | 28 Fri | 29 Sat | 30 Sun | 31 Mon | 01 Tue | 02 Wed | 03 Thu | 04 Fri | 05 Sat | 06 Sun | 07 Mon | 08 Tue | 09 Wed | 10 Thu | 11 Fri | 12 Sat | 13 Sun | 14 Mon | 15 Tue | 16 Wed | 17 Thu | 18 Fri | 19 Sat | 20 Sun | 21 Mon | 22 Tue | 23 Wed | 24 Thu | 25 Fri | 26 Sat | 27 Sun | 28 Mon
1.1 | Phase 1 | Research & Requirements Alignment (Schemas & Photos) | 2026-08-17 | 2026-08-21 | 5 | Not Started
1.2 | Phase 1 | Azure AI & Power Platform Tenant Provisioning | 2026-08-19 | 2026-08-23 | 5 | Not Started
2.1 | Phase 2 | Dataverse Master Tables & Fabric OneLake Setup | 2026-08-24 | 2026-08-28 | 5 | Not Started
2.2 | Phase 2 | AI Document Intelligence & GPT-4o Vision API | 2026-08-26 | 2026-08-30 | 5 | Not Started
3.1 | Phase 3 | Process 1 Build: B2B Quote Approval Automation | 2026-08-31 | 2026-09-06 | 7 | Not Started
3.2 | Phase 3 | Process 2 Build: Warranty Claim & Vision Triage | 2026-09-04 | 2026-09-11 | 8 | Not Started
3.3 | Phase 3 | Copilot Studio Agent Core Orchestration | 2026-09-07 | 2026-09-13 | 7 | Not Started
4.1 | Phase 4 | Pitch Deck & Storyboard (3-6-5 Playbook) | 2026-09-14 | 2026-09-18 | 5 | Not Started
4.2 | Phase 4 | End-to-End Live Integration & Rehearsal | 2026-09-16 | 2026-09-20 | 5 | Not Started
5.1 | Phase 5 | INTERNAL FEATURE FREEZE & Executive Dry Run | 2026-09-21 | 2026-09-25 | 5 | Critical Path
5.2 | Phase 5 | Backup 4K Video Recording (Failsafe Demo) | 2026-09-22 | 2026-09-26 | 5 | Not Started
5.3 | Phase 5 | UOB Summit Event Day & Live Booth Demo | 2026-09-28 | 2026-09-28 | 1 | Milestone | [42 empty] | █
Legend & Phase Color Coding:
| Phase 1: Planning & Setup |  |  | Phase 3: Demo Development |  | Phase 4: Pitch & Polish |  | Phase 5: Freeze & Buffer